## Timeline
POS System: 10-week project timeline
Project start (Monday of week 1) | 2026-07-06 | Plan start date. Change it and every week updates.
Week | Starts | Ends | Focus | Owners | Tasks | Marks component | Status | Evidence
1 | 2026-07-06 | 2026-07-12 | Setup and roles | Subhash, Vrushay | Team repo and report folders, backend upload, role and module allocation, frontend folder structure, GitHub training, idea and abstract. | Idea & Abstract, Weekly Progress, Implementation | Done | 13dc390, 4584088, 80c721c, ef6144e, ddf392b, 751e82d
2 | 2026-07-13 | 2026-07-19 | Design and Redux split | Vrushay, Subhash | UML and ER diagrams (done), Redux Toolkit split: part 1 by Vrushay (done), part 2 and globleState.js by Subhash (in progress). | Design, Implementation | In progress | 11645a2, dbcae3a, 7ab1196 to 9809d35
3 | 2026-07-20 | 2026-07-26 | Super Admin and onboarding | Vrushay (Super Admin), Tanya (onboarding) | Super Admin pages: dashboard, stores, store details, pending requests, subscription plans, settings. Login, forgot password and onboarding. | Implementation | Done | 26 Super Admin commits, 7307504 (onboarding owner details)
4 | 2026-07-27 | 2026-08-02 | Store module | Tanya | Store pages (11): dashboard, branches, categories, employees, products, stores, sales, reports, upgrade, settings, alerts. | Implementation | Done
5 | 2026-08-03 | 2026-08-09 | Branch Manager and Cashier | Vishvas (Branch Manager), Vimal (Cashier) | Branch Manager pages (9) and Cashier pages (5): POS screen, returns, order history, customer lookup, shift summary. | Implementation | Done | 3197520, bb95311, db9c60b, 3d1187e, deff443, 655d718, 2d48633, 7974ef5, 7faddd4, 76a311a
6 | 2026-08-10 | 2026-08-16 | Testing | Vrushay with the whole team | Postman report and 96-case sheet done. Run the collection with all role tokens, record results, negative and security tests, bug fixes. | Testing | In progress | 9e2ca1a, 8172cb7 (report), test case sheet
7 | 2026-08-17 | 2026-08-23 | Payments and integration | Team | Razorpay and Stripe checkout, subscription upgrade, payment status, email receipts, API integration. | Implementation | Planned
8 | 2026-08-24 | 2026-08-30 | Code quality, SRS and documentation | Team | SRS in IEEE format, Axios interceptor, logout fix, API URL in env file, remove console logs, fix security findings, update README. | Implementation & Code Quality | Planned
9 | 2026-08-31 | 2026-09-06 | Presentation and viva prep | Team | Report PPT, demo script, viva questions, final documents. | Presentation, Demo & Viva | Planned
10 | 2026-09-07 | 2026-09-13 | Final demo and submission | Team | Full demo run, final checks, final commit log, submission. | Demo & Viva, Weekly Progress | Planned
Done weeks | 4
In progress | 2
Planned | 4
Formulas:
Starts = B3+7*([Week]-1)
Ends = [Starts]+6

## Frontend work log
Frontend work log: who built which module
Member | GitHub | Module | Pages | Known commits (to 10 Oct) | Status
Vrushay Bohra | bohra0022 | Redux Toolkit part 1, frontend setup, Super Admin, routing | 11 Redux features, API client, utils, 6 Super Admin pages | 45 frontend commits: Super Admin 26, Redux Toolkit 12, Setup 6, Routing 1 | Done
Subhash Dhaka | subhash8729 | Folder structure, Redux Toolkit part 2 | Redux: payment, product, refund, sale, shiftReport, store, storeAnalytics, subscription, subscriptionPlan, transaction, user, globleState.js | 3 frontend commits: Redux Toolkit 1, Setup 2 | In progress
Vimal Kumar | iamvkb7 | Cashier | 5 pages: create order, orders, returns, customers, shift summary | 40 frontend commits | Done
Vishvas Choubisa | choubisavishvas-web | Branch Manager | 9 pages: dashboard, orders, refunds, transactions, inventory, employees, customers, reports, settings | 35 frontend commits | Done
Tanya Singh | tanyasingh077 | Store (largest module) and onboarding | 11 pages: dashboard, branches, categories, employees, products, stores, sales, reports, upgrade, settings, alerts | 11 frontend commits: Store 8, Auth and onboarding 3 | Done
Total pages across modules |  |  | 31
Frontend commits by member and module (from Git, 10 Oct 2026)
Member | Module | Frontend commits
Vrushay Bohra | Super Admin | 26
Vrushay Bohra | Redux Toolkit | 12
Vrushay Bohra | Setup and shared | 6
Vrushay Bohra | Routing | 1
Vimal Kumar | Cashier | 40
Vishvas Choubisa | Branch Manager | 35
Tanya Singh | Store | 8
Tanya Singh | Auth and onboarding | 3
Subhash Dhaka | Setup and shared | 2
Subhash Dhaka | Redux Toolkit | 1
Total |  | 134
Run reports/04-weekly-progress/make_commit_log.py for the latest numbers.

## Done so far
Work completed so far
# | Item | Marks component | Week | Evidence | Status
1 | Team repo and report folders set up | Weekly Progress | 1 | 80c721c, 4584088 | Done
2 | Full Spring Boot backend uploaded | Implementation | 1 | ef6144e | Done
3 | Project idea, abstract and objectives | Idea & Abstract | 1 | see commit_log.csv | Done
4 | Features, modules and tech stack | SRS / Documentation | 1 | 13dc390 | Done
5 | Frontend folder structure (Subhash) | Implementation | 1 | ddf392b, 751e82d | Done
6 | Frontend config, API client and utils (Vrushay) | Implementation | 2 | dbcae3a | Done
7 | Redux Toolkit part 1, 11 features (Vrushay) | Implementation | 2 | 7ab1196 to 9809d35 | Done
8 | Commit log updates | Weekly Progress | 2 | 046f470, 67e0b4c, 8360f7e | Done
9 | UML, ER and architecture diagrams (20) | Design | 2 | 11645a2 | Done
10 | Postman testing report, 2 parts | Testing | 6 | 9e2ca1a, 8172cb7 | Done
11 | README with weekly plan | Weekly Progress | 1 | b0ebffe, cdd3a24, b4bee2d | Done
12 | 10-week timeline and tracker | Weekly Progress | 1 | 75398a4, 28069ac, 65daf38 | Done
13 | Week 1 report and weekly template | Weekly Progress | 1 | 4430a3c, 7ce4830 | Done
14 | API test case sheet (96 cases) | Testing | 6 | POS_Backend_Test_Cases.xlsx | Made, not committed
15 | Branch Manager module (Vishvas) | Implementation | 5 | 3197520, bb95311, db9c60b | Done
16 | Cashier module (Vimal) | Implementation | 5 | 3d1187e, deff443, 655d718, 2d48633, 7974ef5, 7faddd4, 76a311a | Done
17 | Store module and onboarding (Tanya) | Implementation | 4 | 7307504 | Done
18 | Super Admin module (Vrushay) | Implementation | 3 | 26 commits, see frontend_work_log.csv | Done
19 | Redux Toolkit part 2 and globleState.js (Subhash) | Implementation | 2 | 1 commit so far | In progress
20 | Run the Postman collection and record results | Testing | 6 | test case sheet | In progress
| Done | 17
| Made, not committed | 1
| In progress | 2
| Pending | 0

## Marks tracker
Progress by marks component
Component | Marks | Status | Notes
Idea & Abstract | 5 | Done | Committed in reports.
SRS / Documentation | 10 | Not started | IEEE format SRS still to be written.
Design (Use-case, Class, ER) | 10 | Done | 20 diagrams committed.
Weekly Progress (tracking sheet) | 25 | Started | Commit log, frontend work log, timeline and weekly reports. Update every week.
Implementation & Code Quality | 20 | Started | Backend and four frontend modules done. Redux part 2 and code quality fixes pending.
Testing | 10 | Started | Report and 96 test cases written, results to be recorded.
Presentation | 10 | Not started
Demo & Viva (individual) | 10 | Not started
Total marks | 100
Marks with work started or done | 70
Share of marks started | 70%